## Week plan
Hours | [5 empty] | Date | Day
[6 empty] | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03 | 2017-11-04
Function | Resource | PM | Client | Project | Task | Mon | Tue | Wed | Thu | Fri | Sat
BD | Mithu |  |  |  |  | 9 | 8 |  | 8 | 8
|  | Mithu | Presales | Internal | Twitter Links and Prep for Next Week | 1
[5 empty] | LinkedIn Banner Advertisement |  |  |  | 2
[5 empty] | Corporate Slide Deck - All slides |  | 2
[5 empty] | Capability Deck - VR, AR |  |  |  | 2 | 2
[5 empty] | PreSales Folder Restructuing |  |  |  |  | 3
[5 empty] | LinkedIn Landing Page Coordination |  |  |  | 2
[5 empty] | Merck - Keytruda Proposal - US | 8
[5 empty] | Merck - Slides Platform - US |  | 3
[5 empty] | Lundbeck - New Proposal - UAE |  | 3
[5 empty] | Market Research - Digital Production and New Ideas |  |  |  | 2 | 3
Content | Anu |  |  |  |  | 9 | 9 |  | 9 | 9
|  | Kavya | Amgen | BABS | PPT formatting | 4
|  | Snehal | Mundipharma | MIM | Response to request | 5 | 9 |  | 9 | 9
| Kumar |  |  |  |  | 9 | 9 |  | 9 | 9 | 14
|  | Kavya | Amgen | BABS | Calls and emails | 2
[5 empty] | PPT Review | 7
[5 empty] | Meeting Attendance |  | 9 |  | 9 | 9 | 9
[5 empty] | Travel back to India | [5 empty] | 5
| Nishi |  |  |  |  | 9 | 9 |  | 9 | 9
|  | Kavya | Amgen | BABS | PPT formatting | 4
|  | Snehal | Mundipharma | MIM | Response to request | 5 | 9 |  | 9 | 9
| Rajesh |  |  |  |  | 9 | 9 |  | 9 | 9 | 14
|  | Kavya | Amgen | BABS | Calls and emails | 2
[5 empty] | PPT Review | 5
[5 empty] | Meeting Attendance |  | 9 |  | 9 | 9 | 9
[5 empty] | Travel back to India | [5 empty] | 5
|  | Snehal | Mundipharma | MIM | Response to request | 2
Creative | Sandy |  |  |  |  | 9 | 9
|  | Kavya | Amgen | BABS | Collateral artwork | 9 | 4
[5 empty] | Presentating formating |  | 5
| Vinoth |  |  |  |  | 3 | 2 |  | 4.2
|  | Kavya | Novartis | Entresto webcast Extension | Webcast teaser development |  |  |  | 3
[5 empty] | Development of remaining creatives |  |  |  | 1
[5 empty] | Addressing of comments of creatives |  |  |  | 0.2
|  | Hari | Bayer | Bayer videos | Creative check on video |  | 2
|  | Hari | Novartis | HART | Creative edits | 3
Ops | Shijin |  |  |  |  | 4 | 4 |  | 4 | 4
|  | (blank) | Internal | Admin Support | Operation Support |  |  |  |  | 3
|  | Shijin | Internal | Admin Support | Operation Support | 3 | 3 |  | 3
|  |  |  | Finance review | Operation Support | 1 | 1 |  | 1 | 1
PM | Hanisha |  |  |  |  | 9.1 | 9.5 |  | 6.5 | 6.5
|  | Kavya | Novartis | AR Videos | Co-ordinate for incorporating the feedback | 2 |  |  | 2 | 2
[5 empty] | Share the VO with Shaik to integrate on the app | 0.5
[5 empty] | Follow up with prince for updated VO | 0.15
|  | Hanisha | Internal | Internal | Project review |  |  |  | 0.5
[5 empty] | Workplan |  |  |  |  | 1
[5 empty] | Follow up with Farrag for sign off on the proposal | 0.15
[5 empty] | Share the updated proposal | 0.5
|  |  |  | Internal | Checking & Responding to E-mails | 0.5 | 0.5 |  | 0.5 | 0.5
[5 empty] | Server hygiene | 1 | 4
[5 empty] | CSR research |  |  |  | 3 | 3
|  |  | Novartis | ICA | Follow up for the Emotions & gestures packages from Imran | 0.5
[5 empty] | Follow up with Alex for approval fo Watson Integration | 0.15
[5 empty] | Kick-off with FWS | 1
|  |  |  | ICA Arabic | Follow up with FWS for a detailed workflow & project plan | 0.15
[5 empty] | Update project plan and timelines |  | 1
[5 empty] | Project briefing document |  | 1
[5 empty] | Sign-off from Vimal & Shijin for the project briefing document |  | 0.5
[5 empty] | Share the project briefing document with FWS |  | 0.5
|  |  | Takeda | Sep Entyvio Adboard | Follow up with Farrag to take up the survey | 0.5
[5 empty] | OSD Finalization | 0.5
|  |  | AZ | 360 Clinical Immersion | Follow up with Dipal for missing contrent in Brazil workshop |  |  |  | 0.5
|  | Hari | Novartis | HART | Co-ordinate with Surendhar for VO integration | 0.5
[5 empty] | Co-ordinate with Surendhar for incorporation of med comments | 1
|  | Sumesh | Internal | Internal | Audit |  | 2
| Hari |  |  |  |  | 5.75 | 6.5 |  | 8.25 | 5
|  | Hari | Novartis | Client call | Follow up with Flieschmann about their call with Novartis |  |  |  | 0.25
|  |  |  | HART | Prepare the report |  |  |  | 1
|  |  |  | Voltaren MCM | Follow up with Portugal team | 0.25
|  |  | Internal | Internal | Checking mails | 0.5 | 0.5 |  | 0.5 | 0.5
[5 empty] | Create workplan |  |  |  | 0.5
[5 empty] | Review Hanisha's activities for the day | 0.5 | 0.5 |  | 0.5 | 0.5
[5 empty] | Review Hanisha's workplan |  |  |  |  | 0.5
[5 empty] | Project review |  |  |  | 1
[5 empty] | Induction | 1 | 1 |  | 1 | 1
[5 empty] | Internal audit |  | 2
|  |  |  | Twitter feed | Search for articles | 0.5 | 0.5 |  | 0.5 | 0.5
|  |  | Bayer | Bayer videos | Coordinate with all teams | 2 | 2 |  | 2 | 2
[5 empty] | Preparing meeting minutes |  |  |  | 1
[5 empty] | Call with Danielle | 1
| Jayanth |  |  |  |  | 9 | 9 | 9 | 9 | 9 | 9
|  | Kavya | Amgen | BABS | Preparation for event | 9 | 4
[5 empty] | Travel to Dubai |  | 5
[5 empty] | Onsite preparation |  |  | 9
[5 empty] | Day 1 meeting attendance |  |  |  | 9
[5 empty] | Day 2 meeting attendance |  |  |  |  | 9
[5 empty] | Day 3 meeting attendance | [5 empty] | 9
| Kavya |  |  |  |  | 9 | 9 | 9 | 9 | 9 | 14
|  | Kavya | Amgen | BABS | Preparation for event | 9 | 4
[5 empty] | Travel to Dubai |  | 5
[5 empty] | Onsite preparation |  |  | 9
[5 empty] | Day 1 meeting attendance |  |  |  | 9
[5 empty] | Day 2 meeting attendance |  |  |  |  | 9
[5 empty] | Day 3 meeting attendance | [5 empty] | 9
[5 empty] | Travel back to India | [5 empty] | 5
| Shijin |  |  |  |  | 4 | 4 |  | 3 | 3
|  | Shijin | Internal | ECE | ECE Project | 4 | 4 |  | 3 | 3
| Swathi |  |  |  |  | 9.65 | 10.35 |  | 7.85 | 9.55
|  | Kavya | Novartis | Entresto webcast Extension | Gather of assests for December speakers (Sipahi and Chu) | 0.1 | 0.1
[5 empty] | Share of 1st IFF |  | 0.1
[5 empty] | Review of comments addressed |  |  |  |  | 1.5
[5 empty] | Share of 2nd IFF |  |  |  |  | 0.1
[5 empty] | To cordinate with Surendhar for drop down integration to website | 0.5 | 0.5
[5 empty] | Dossier development | 1
[5 empty] | Development of Status update report |  |  |  |  | 0.5
[5 empty] | PR of Nov 08 Asia & MENA websites |  | 3
[5 empty] | Follow up to have comments fixed |  |  |  | 0.1
[5 empty] | Receive Signed CBF and save to server | 0.1 | 0.1
[5 empty] | Reminder to faculty for sharing his PPT | 0.5
[5 empty] | Share of Faculty contract | 0.1 | 0.1
[5 empty] | Reminder for Joao to open 2 job bag | 0.1
[5 empty] | To ensure the job bag is open |  | 0.1
[5 empty] | Upload of faculty PPT to ZINC |  |  |  | 0.2 | 0.2
[5 empty] | Share of faculty ppt for internal review |  |  |  | 0.1 | 0.1
[5 empty] | Compile of faculty PPT comments and ensure to share with faculty |  |  |  |  | 0.1
[5 empty] | Honorarium calculation for Dec Asia speaker (Taiwan) |  |  |  |  | 0.5
[5 empty] | Honorarium calculation for Dec MENA speaker (Turkey) |  |  |  |  | 0.5
[5 empty] | Development of CBF for Dec Asia Speaker (Taiwan) |  |  |  |  | 0.5
[5 empty] | Development of CBF for Dec MENA Speaker (Turkey) |  |  |  |  | 0.5
[5 empty] | PR of creatives |  |  |  |  | 0.5
[5 empty] | Briefing call with Dr Po Chu | 1
[5 empty] | MoM of briefing call with Dr Po Chu | 1
[5 empty] | Sign off on creatives |  |  |  |  | 0.2
[5 empty] | Webcast teaser # 7 development content review |  | 0.1
[5 empty] | Follow up with faculty for PPT |  |  |  | 0.1 | 0.1
|  |  |  | Entresto webcast series | Folder review | 1 |  |  |  | 1
|  |  | Eli Lilly | Equip 2017 | Development of monthly report |  |  |  | 6
|  |  |  | Equip Iraq & Lebanon | Monitor queries | 0.25 | 0.25 |  | 0.25 | 0.25
[5 empty] | Development of monthly report |  | 4
[5 empty] | Development of Status update report |  | 0.5
|  | Swathi | Novartis | HF case player | To cordinate with Snehal and Kumar for the change in porposal according to client requirement | 1 | 1
[5 empty] | Project initation steps |  |  |  |  | 2
[5 empty] | Development of Status update report |  | 0.5
|  |  | Internal | Internal | Intenal presentation preparation | 2 |  |  | 1
|  |  |  | Workplan | Request PM for workplan's |  |  |  | 0.1
[5 empty] | Compile weekly plan | 1 |  |  |  | 1
QC | Sumesh |  |  |  |  | 9 | 10 |  | 9 | 6.5
|  | Kavya | Novartis | Entresto webcast Extension | QC of creatives |  |  |  | 0.5
[5 empty] | Review of comments addressed |  |  |  |  | 1.5
[5 empty] | Sign off on drop down column intergration |  |  |  | 0.5
[5 empty] | QC of Nov 08 Asia & MENA websites |  |  |  | 3
|  |  | Amgen | BABS | QC of presentation | 9
[5 empty] | Qc of print material |  | 6
|  |  | Eli Lilly | Equip 2017 | Module player design and development |  |  |  | 5 | 5
|  | Hari | Novartis | HART | QC of accreditation certification |  | 1
[5 empty] | Final QC |  | 1
|  |  | Bayer | Bayer videos | QC of creatives |  | 2
Grand Total | [5 empty] | 116.5 | 117.35 | 18 | 104.8 | 96.55 | 51

## Summary
Row Labels | Planned Hours | Actual hours | Available
Anu | 36 | 40 | 4
Hanisha | 31.6 | 36 | 4.4
Hari | 25.5 | 36 | 10.5
Jayanth | 54 | 54 | 0
Kavya | 59 | 54 | -5
Kumar | 50 | 36 | -14
Mithu | 33 | 36 | 3
Nishi | 36 | 36 | 0
Rajesh | 50 | 36 | -14
Sandy | 18 | 36 | 18
Shijin | 30 | 36 | 6
Sumesh | 34.5 | 36 | 1.5
Swathi | 37.4 | 36 | -1.4
Vinoth | 9.2 | 36 | 26.8
Grand Total | 504.2 | 544 | 39.8

## Raw plan
Client | PM | Project | Date | Day | Resource | Task | Hours | Function
Mundipharma | Snehal | MIM | 2017-10-30 | Mon | Rajesh | Response to request | 2 | Content
Amgen | Kavya | BABS | 2017-10-30 | Mon | Rajesh | Calls and emails | 2 | Content
Amgen | Kavya | BABS | 2017-10-30 | Mon | Rajesh | PPT Review | 5 | Content
Amgen | Kavya | BABS | 2017-10-31 | Tue | Rajesh | Meeting Attendance | 9 | Content
Amgen | Kavya | BABS | 2017-11-02 | Thu | Rajesh | Meeting Attendance | 9 | Content
Amgen | Kavya | BABS | 2017-11-03 | Fri | Rajesh | Meeting Attendance | 9 | Content
Amgen | Kavya | BABS | 2017-10-30 | Mon | Kumar | Calls and emails | 2 | Content
Amgen | Kavya | BABS | 2017-10-30 | Mon | Kumar | PPT Review | 7 | Content
Amgen | Kavya | BABS | 2017-10-31 | Tue | Kumar | Meeting Attendance | 9 | Content
Amgen | Kavya | BABS | 2017-11-02 | Thu | Kumar | Meeting Attendance | 9 | Content
Amgen | Kavya | BABS | 2017-11-03 | Fri | Kumar | Meeting Attendance | 9 | Content
Mundipharma | Snehal | MIM | 2017-10-30 | Mon | Anu | Response to request | 5 | Content
Amgen | Kavya | BABS | 2017-10-30 | Mon | Anu | PPT formatting | 4 | Content
Mundipharma | Snehal | MIM | 2017-10-31 | Tue | Anu | Response to request | 9 | Content
Mundipharma | Snehal | MIM | 2017-11-02 | Thu | Anu | Response to request | 9 | Content
Mundipharma | Snehal | MIM | 2017-11-03 | Fri | Anu | Response to request | 9 | Content
Mundipharma | Snehal | MIM | 2017-10-30 | Mon | Nishi | Response to request | 5 | Content
Amgen | Kavya | BABS | 2017-10-30 | Mon | Nishi | PPT formatting | 4 | Content
Mundipharma | Snehal | MIM | 2017-10-31 | Tue | Nishi | Response to request | 9 | Content
Mundipharma | Snehal | MIM | 2017-11-02 | Thu | Nishi | Response to request | 9 | Content
Mundipharma | Snehal | MIM | 2017-11-03 | Fri | Nishi | Response to request | 9 | Content
Internal | Hanisha | Internal | 2017-10-30 | Mon | Hanisha | Checking & Responding to E-mails | 0.5 | PM
Internal | Hanisha | Internal | 2017-10-31 | Tue | Hanisha | Checking & Responding to E-mails | 0.5 | PM
Internal | Hanisha | Internal | 2017-11-02 | Thu | Hanisha | Checking & Responding to E-mails | 0.5 | PM
Internal | Hanisha | Internal | 2017-11-03 | Fri | Hanisha | Checking & Responding to E-mails | 0.5 | PM
Novartis | Hanisha | ICA | 2017-10-30 | Mon | Hanisha | Follow up with Alex for approval fo Watson Integration | 0.15 | PM
Novartis | Hanisha | ICA | 2017-10-30 | Mon | Hanisha | Follow up for the Emotions & gestures packages from Imran | 0.5 | PM
Novartis | Hanisha | ICA Arabic | 2017-10-31 | Tue | Hanisha | Update project plan and timelines | 1 | PM
Novartis | Hanisha | ICA Arabic | 2017-10-31 | Tue | Hanisha | Project briefing document | 1 | PM
Novartis | Hanisha | ICA Arabic | 2017-10-30 | Mon | Hanisha | Follow up with FWS for a detailed workflow & project plan | 0.15 | PM
Novartis | Hanisha | ICA Arabic | 2017-10-31 | Tue | Hanisha | Sign-off from Vimal & Shijin for the project briefing document | 0.5 | PM
Novartis | Hanisha | ICA Arabic | 2017-10-31 | Tue | Hanisha | Share the project briefing document with FWS | 0.5 | PM
Internal | Hanisha | Internal | 2017-10-30 | Mon | Hanisha | Follow up with Farrag for sign off on the proposal | 0.15 | PM
Internal | Hanisha | Internal | 2017-10-30 | Mon | Hanisha | Share the updated proposal | 0.5 | PM
Takeda | Hanisha | Sep Entyvio Adboard | 2017-10-30 | Mon | Hanisha | Follow up with Farrag to take up the survey | 0.5 | PM
Takeda | Hanisha | Sep Entyvio Adboard | 2017-10-30 | Mon | Hanisha | OSD Finalization | 0.5 | PM
Novartis | Hanisha | ICA | 2017-10-30 | Mon | Hanisha | Kick-off with FWS | 1 | PM
Internal | Hanisha | Internal | 2017-11-02 | Thu | Hanisha | Project review | 0.5 | PM
Internal | Hanisha | Internal | 2017-11-03 | Fri | Hanisha | Workplan | 1 | PM
Novartis | Kavya | AR Videos | 2017-10-30 | Mon | Hanisha | Co-ordinate for incorporating the feedback | 2 | PM
Novartis | Kavya | AR Videos | 2017-11-02 | Thu | Hanisha | Co-ordinate for incorporating the feedback | 2 | PM
Novartis | Kavya | AR Videos | 2017-11-03 | Fri | Hanisha | Co-ordinate for incorporating the feedback | 2 | PM
Novartis | Kavya | AR Videos | 2017-10-30 | Mon | Hanisha | Share the VO with Shaik to integrate on the app | 0.5 | PM
Novartis | Kavya | AR Videos | 2017-10-30 | Mon | Hanisha | Follow up with prince for updated VO | 0.15 | PM
AZ | Hanisha | 360 Clinical Immersion | 2017-11-02 | Thu | Hanisha | Follow up with Dipal for missing contrent in Brazil workshop | 0.5 | PM
Novartis | Hari | HART | 2017-10-30 | Mon | Vinoth | Creative edits | 3 | Creative
Novartis | Hari | HART | 2017-10-30 | Mon | Hanisha | Co-ordinate with Surendhar for VO integration | 0.5 | PM
Novartis | Hari | HART | 2017-10-30 | Mon | Hanisha | Co-ordinate with Surendhar for incorporation of med comments | 1 | PM
Internal | Hanisha | Internal | 2017-10-30 | Mon | Hanisha | Server hygiene | 1 | PM
Internal | Hanisha | Internal | 2017-10-31 | Tue | Hanisha | Server hygiene | 4 | PM
Internal | Sumesh | Internal | 2017-10-31 | Tue | Hanisha | Audit | 2 | PM
Internal | Hanisha | Internal | 2017-11-02 | Thu | Hanisha | CSR research | 3 | PM
Internal | Hanisha | Internal | 2017-11-03 | Fri | Hanisha | CSR research | 3 | PM
Internal | Hari | Internal | 2017-10-30 | Mon | Hari | Checking mails | 0.5 | PM
Internal | Hari | Internal | 2017-10-31 | Tue | Hari | Checking mails | 0.5 | PM
Internal | Hari | Internal | 2017-11-02 | Thu | Hari | Checking mails | 0.5 | PM
Internal | Hari | Internal | 2017-11-03 | Fri | Hari | Checking mails | 0.5 | PM
Internal | Hari | Internal | 2017-10-30 | Mon | Hari | Review Hanisha's activities for the day | 0.5 | PM
Internal | Hari | Internal | 2017-10-31 | Tue | Hari | Review Hanisha's activities for the day | 0.5 | PM
Internal | Hari | Internal | 2017-11-02 | Thu | Hari | Review Hanisha's activities for the day | 0.5 | PM
Internal | Hari | Internal | 2017-11-03 | Fri | Hari | Review Hanisha's activities for the day | 0.5 | PM
Internal | Hari | Internal | 2017-11-03 | Fri | Hari | Review Hanisha's workplan | 0.5 | PM
Internal | Hari | Internal | 2017-11-02 | Thu | Hari | Create workplan | 0.5 | PM
Novartis | Hari | HART | 2017-11-02 | Thu | Hari | Prepare the report | 1 | PM
Novartis | Hari | HART | 2017-10-31 | Tue | Sumesh | QC of accreditation certification | 1 | QC
Novartis | Hari | HART | 2017-10-31 | Tue | Sumesh | Final QC | 1 | QC
Novartis | Hari | Voltaren MCM | 2017-10-30 | Mon | Hari | Follow up with Portugal team | 0.25 | PM
Novartis | Hari | Client call | 2017-11-02 | Thu | Hari | Follow up with Flieschmann about their call with Novartis | 0.25 | PM
Bayer | Hari | Bayer videos | 2017-10-30 | Mon | Hari | Coordinate with all teams | 2 | PM
Bayer | Hari | Bayer videos | 2017-10-31 | Tue | Hari | Coordinate with all teams | 2 | PM
Bayer | Hari | Bayer videos | 2017-11-02 | Thu | Hari | Coordinate with all teams | 2 | PM
Bayer | Hari | Bayer videos | 2017-11-03 | Fri | Hari | Coordinate with all teams | 2 | PM
Bayer | Hari | Bayer videos | 2017-11-02 | Thu | Hari | Preparing meeting minutes | 1 | PM
Bayer | Hari | Bayer videos | 2017-10-31 | Tue | Vinoth | Creative check on video | 2 | Creative
Bayer | Hari | Bayer videos | 2017-10-31 | Tue | Sumesh | QC of creatives | 2 | QC
Bayer | Hari | Bayer videos | 2017-10-30 | Mon | Hari | Call with Danielle | 1 | PM
Internal | Hari | Twitter feed | 2017-10-30 | Mon | Hari | Search for articles | 0.5 | PM
Internal | Hari | Twitter feed | 2017-10-31 | Tue | Hari | Search for articles | 0.5 | PM
Internal | Hari | Twitter feed | 2017-11-02 | Thu | Hari | Search for articles | 0.5 | PM
Internal | Hari | Twitter feed | 2017-11-03 | Fri | Hari | Search for articles | 0.5 | PM
Internal | Hari | Internal | 2017-10-30 | Mon | Hari | Induction | 1 | PM
Internal | Hari | Internal | 2017-10-31 | Tue | Hari | Induction | 1 | PM
Internal | Hari | Internal | 2017-11-02 | Thu | Hari | Induction | 1 | PM
Internal | Hari | Internal | 2017-11-03 | Fri | Hari | Induction | 1 | PM
Internal | Hari | Internal | 2017-10-31 | Tue | Hari | Internal audit | 2 | PM
Internal | Hari | Internal | 2017-11-02 | Thu | Hari | Project review | 1 | PM
Internal | Shijin | ECE | 2017-10-30 | Mon | Shijin | ECE Project | 4 | PM
Internal | Shijin | ECE | 2017-10-31 | Tue | Shijin | ECE Project | 4 | PM
Internal | Shijin | ECE | 2017-11-02 | Thu | Shijin | ECE Project | 3 | PM
Internal | Shijin | ECE | 2017-11-03 | Fri | Shijin | ECE Project | 3 | PM
Internal | Shijin | Finance review | 2017-10-30 | Mon | Shijin | Operation Support | 1 | Ops
Internal | Shijin | Admin Support | 2017-10-30 | Mon | Shijin | Operation Support | 3 | Ops
Internal | Shijin | Finance review | 2017-10-31 | Tue | Shijin | Operation Support | 1 | Ops
Internal | Shijin | Admin Support | 2017-10-31 | Tue | Shijin | Operation Support | 3 | Ops
Internal | Shijin | Finance review | 2017-11-02 | Thu | Shijin | Operation Support | 1 | Ops
Internal | Shijin | Admin Support | 2017-11-02 | Thu | Shijin | Operation Support | 3 | Ops
Internal | Shijin | Finance review | 2017-11-03 | Fri | Shijin | Operation Support | 1 | Ops
Internal |  | Admin Support | 2017-11-03 | Fri | Shijin | Operation Support | 3 | Ops
Eli Lilly | Kavya | Equip Iraq & Lebanon | 2017-10-30 | Mon | Swathi | Monitor queries | 0.25 | PM
Eli Lilly | Kavya | Equip Iraq & Lebanon | 2017-10-31 | Tue | Swathi | Monitor queries | 0.25 | PM
Eli Lilly | Kavya | Equip Iraq & Lebanon | 2017-11-02 | Thu | Swathi | Monitor queries | 0.25 | PM
Eli Lilly | Kavya | Equip Iraq & Lebanon | 2017-11-03 | Fri | Swathi | Monitor queries | 0.25 | PM
Internal | Swathi | Workplan | 2017-11-02 | Thu | Swathi | Request PM for workplan's | 0.1 | PM
Internal | Swathi | Workplan | 2017-11-03 | Fri | Swathi | Compile weekly plan | 1 | PM
Internal | Swathi | Workplan | 2017-10-30 | Mon | Swathi | Compile weekly plan | 1 | PM
Eli Lilly | Kavya | Equip 2017 | 2017-11-02 | Thu | Swathi | Development of monthly report | 6 | PM
Eli Lilly | Kavya | Equip Iraq & Lebanon | 2017-10-31 | Tue | Swathi | Development of monthly report | 4 | PM
Eli Lilly | Kavya | Equip Iraq & Lebanon | 2017-10-31 | Tue | Swathi | Development of Status update report | 0.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Development of Status update report | 0.5 | PM
Novartis | Swathi | HF case player | 2017-10-31 | Tue | Swathi | Development of Status update report | 0.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-31 | Tue | Swathi | PR of Nov 08 Asia & MENA websites | 3 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-02 | Thu | Sumesh | QC of Nov 08 Asia & MENA websites | 3 | QC
Novartis | Kavya | Entresto webcast Extension | 2017-10-31 | Tue | Swathi | Share of 1st IFF | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-02 | Thu | Swathi | Follow up to have comments fixed | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Review of comments addressed | 1.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Sumesh | Review of comments addressed | 1.5 | QC
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Share of 2nd IFF | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-30 | Mon | Swathi | To cordinate with Surendhar for drop down integration to website | 0.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-31 | Tue | Swathi | To cordinate with Surendhar for drop down integration to website | 0.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-02 | Thu | Sumesh | Sign off on drop down column intergration | 0.5 | QC
Novartis | Kavya | Entresto webcast Extension | 2017-10-30 | Mon | Swathi | Receive Signed CBF and save to server | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-31 | Tue | Swathi | Receive Signed CBF and save to server | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-30 | Mon | Swathi | Reminder to faculty for sharing his PPT | 0.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-02 | Thu | Swathi | Follow up with faculty for PPT | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Follow up with faculty for PPT | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-30 | Mon | Swathi | Share of Faculty contract | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-31 | Tue | Swathi | Share of Faculty contract | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-30 | Mon | Swathi | Reminder for Joao to open 2 job bag | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-31 | Tue | Swathi | To ensure the job bag is open | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-02 | Thu | Swathi | Upload of faculty PPT to ZINC | 0.2 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Upload of faculty PPT to ZINC | 0.2 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-02 | Thu | Swathi | Share of faculty ppt for internal review | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Share of faculty ppt for internal review | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Compile of faculty PPT comments and ensure to share with faculty | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-30 | Mon | Swathi | Gather of assests for December speakers (Sipahi and Chu) | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-31 | Tue | Swathi | Gather of assests for December speakers (Sipahi and Chu) | 0.1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Honorarium calculation for Dec Asia speaker (Taiwan) | 0.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Honorarium calculation for Dec MENA speaker (Turkey) | 0.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Development of CBF for Dec Asia Speaker (Taiwan) | 0.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Development of CBF for Dec MENA Speaker (Turkey) | 0.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-30 | Mon | Swathi | Dossier development | 1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-02 | Thu | Vinoth | Webcast teaser development | 3 | Creative
Novartis | Kavya | Entresto webcast Extension | 2017-11-02 | Thu | Vinoth | Development of remaining creatives | 1 | Creative
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | PR of creatives | 0.5 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-02 | Thu | Sumesh | QC of creatives | 0.5 | QC
Novartis | Kavya | Entresto webcast Extension | 2017-11-02 | Thu | Vinoth | Addressing of comments of creatives | 0.2 | Creative
Novartis | Kavya | Entresto webcast Extension | 2017-10-30 | Mon | Swathi | Briefing call with Dr Po Chu | 1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-30 | Mon | Swathi | MoM of briefing call with Dr Po Chu | 1 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-11-03 | Fri | Swathi | Sign off on creatives | 0.2 | PM
Novartis | Kavya | Entresto webcast Extension | 2017-10-31 | Tue | Swathi | Webcast teaser # 7 development content review | 0.1 | PM
Novartis | Kavya | Entresto webcast series | 2017-11-03 | Fri | Swathi | Folder review | 1 | PM
Novartis | Kavya | Entresto webcast series | 2017-10-30 | Mon | Swathi | Folder review | 1 | PM
Novartis | Swathi | HF case player | 2017-10-30 | Mon | Swathi | To cordinate with Snehal and Kumar for the change in porposal according to client requirement | 1 | PM
Novartis | Swathi | HF case player | 2017-10-31 | Tue | Swathi | To cordinate with Snehal and Kumar for the change in porposal according to client requirement | 1 | PM
Novartis | Swathi | HF case player | 2017-11-03 | Fri | Swathi | Project initation steps | 2 | PM
Internal | Swathi | Internal | 2017-11-02 | Thu | Swathi | Intenal presentation preparation | 1 | PM
Internal | Swathi | Internal | 2017-10-30 | Mon | Swathi | Intenal presentation preparation | 2 | PM
Presales | Mithu | Internal | 2017-10-30 | Mon | Mithu | Merck - Keytruda Proposal - US | 8 | BD
Presales | Mithu | Internal | 2017-10-30 | Mon | Mithu | Twitter Links and Prep for Next Week | 1 | BD
Presales | Mithu | Internal | 2017-10-31 | Tue | Mithu | Lundbeck - New Proposal - UAE | 3 | BD
Presales | Mithu | Internal | 2017-10-31 | Tue | Mithu | Merck - Slides Platform - US | 3 | BD
Presales | Mithu | Internal | 2017-10-31 | Tue | Mithu | Corporate Slide Deck - All slides | 2 | BD
Presales | Mithu | Internal | 2017-11-02 | Thu | Mithu | LinkedIn Banner Advertisement | 2 | BD
Presales | Mithu | Internal | 2017-11-02 | Thu | Mithu | LinkedIn Landing Page Coordination | 2 | BD
Presales | Mithu | Internal | 2017-11-02 | Thu | Mithu | Capability Deck - VR, AR | 2 | BD
Presales | Mithu | Internal | 2017-11-02 | Thu | Mithu | Market Research - Digital Production and New Ideas | 2 | BD
Presales | Mithu | Internal | 2017-11-03 | Fri | Mithu | PreSales Folder Restructuing | 3 | BD
Presales | Mithu | Internal | 2017-11-03 | Fri | Mithu | Market Research - Digital Production and New Ideas | 3 | BD
Presales | Mithu | Internal | 2017-11-03 | Fri | Mithu | Capability Deck - VR, AR | 2 | BD
Amgen | Kavya | BABS | 2017-10-30 | Mon | Kavya | Preparation for event | 9 | PM
Amgen | Kavya | BABS | 2017-10-31 | Tue | Kavya | Preparation for event | 4 | PM
Amgen | Kavya | BABS | 2017-10-31 | Tue | Kavya | Travel to Dubai | 5 | PM
Amgen | Kavya | BABS | 2017-11-01 | Wed | Kavya | Onsite preparation | 9 | PM
Amgen | Kavya | BABS | 2017-11-02 | Thu | Kavya | Day 1 meeting attendance | 9 | PM
Amgen | Kavya | BABS | 2017-11-03 | Fri | Kavya | Day 2 meeting attendance | 9 | PM
Amgen | Kavya | BABS | 2017-11-04 | Sat | Kavya | Day 3 meeting attendance | 9 | PM
Amgen | Kavya | BABS | 2017-11-04 | Sat | Kavya | Travel back to India | 5 | PM
Amgen | Kavya | BABS | 2017-11-04 | Sat | Kumar | Travel back to India | 5 | Content
Amgen | Kavya | BABS | 2017-11-04 | Sat | Rajesh | Travel back to India | 5 | Content
Amgen | Kavya | BABS | 2017-10-30 | Mon | Jayanth | Preparation for event | 9 | PM
Amgen | Kavya | BABS | 2017-10-31 | Tue | Jayanth | Preparation for event | 4 | PM
Amgen | Kavya | BABS | 2017-10-31 | Tue | Jayanth | Travel to Dubai | 5 | PM
Amgen | Kavya | BABS | 2017-11-01 | Wed | Jayanth | Onsite preparation | 9 | PM
Amgen | Kavya | BABS | 2017-11-02 | Thu | Jayanth | Day 1 meeting attendance | 9 | PM
Amgen | Kavya | BABS | 2017-11-03 | Fri | Jayanth | Day 2 meeting attendance | 9 | PM
Amgen | Kavya | BABS | 2017-11-04 | Sat | Jayanth | Day 3 meeting attendance | 9 | PM
Amgen | Kavya | BABS | 2017-11-04 | Sat | Kumar | Meeting Attendance | 9 | Content
Amgen | Kavya | BABS | 2017-11-04 | Sat | Rajesh | Meeting Attendance | 9 | Content
Amgen | Kavya | BABS | 2017-10-30 | Mon | Sandy | Collateral artwork | 9 | Creative
Amgen | Kavya | BABS | 2017-10-31 | Tue | Sandy | Collateral artwork | 4 | Creative
Amgen | Kavya | BABS | 2017-10-31 | Tue | Sandy | Presentating formating | 5 | Creative
Amgen | Kavya | BABS | 2017-10-30 | Mon | Sumesh | QC of presentation | 9 | QC
Amgen | Kavya | BABS | 2017-10-31 | Tue | Sumesh | Qc of print material | 6 | QC
Eli Lilly | Kavya | Equip 2017 | 2017-11-02 | Thu | Sumesh | Module player design and development | 5 | QC
Eli Lilly | Kavya | Equip 2017 | 2017-11-03 | Fri | Sumesh | Module player design and development | 5 | QC